## Lists
Project Status Options | RAG Status (Red–Amber–Green) | Priority Levels | Impact / Effort Ratings | Owners or Responsible Persons
Not Started | Red | Low | Low | Purnima
In Progress | Amber | Medium | Medium | Hannah
At Risk | Green | High | High
Delayed |  | Critical
Completed
On Hold

## Digital Mktg & Comms 2026
Digital Marketing & Communications Project Plan 2026
Project Overview | Create a unified digital marketing and communications plan for stronger awareness, engagement, and fundraising.
Goals & KPIs | Increase awareness, engagement, and campaign performance using clear monthly metrics.
Scope | All digital, marketing, comms, content, and campaign activities; excludes non-marketing tasks.
Stakeholder List | Comms, Fundraising, Services, Leadership, Yellow Harbour, and external suppliers.
Risks & Dependencies | Resource limits, partner delays, data issues, and cross-team dependencies.
Pillars | Phase | # | Description | Assigned to | Dependency | Start Date | Completed by | Duration (days) | Status | RAG | Priority | % Complete | Notes
Website Re-building (ARC Website Upgrade Project) | Website Audit & Discovery | 1 | Conduct a full audit of current website: structure, navigation, content quality, UX, SEO, accessibility, and page performance. | Purnima | Self/Agency | 2025-11-21 | 2025-12-24 | 24 | In Progress
|  | 2 | Create a page inventory and tag areas needing improvement (content gaps, formatting issues, design inconsistencies). | Purnima | Developer | 2025-11-21 | 2025-12-24 | 24 | In Progress
| Template & Component Planning | 1 | Review existing templates; decide which can be reused and which need redesign. | Purnima | Self | 2025-11-21 | 2025-12-24 | 24 | In Progress
|  | 2 | Draft new wireframes/templates aligned with ARC’s Brand Messaging Guide. | Purnima | Self | 2025-12-26 | 2026-01-30 | 36 | Not Started
| CMS Platform Migration (with external partner) | 1 | Work with the CMS optimisation partner to migrate ARC’s website to the new platform (faster, customisable, SEO-friendly). | Purnima | Agency Partner | 2025-12-26 | 2026-01-30 | 36 | Not Started
|  | 2 | Implement components that allow ARC to manage sections easily (custom blocks, layouts, improved editor tools). | Purnima | Agency Partner | 2025-12-26 | 2026-01-30 | 36 | Not Started
| Build, Test & Optimise | 1 | Build new pages using the updated templates; optimise speed, accessibility, and mobile-first design. | Purnima | Self | 2025-12-26 | 2026-02-27 | 64 | Not Started
|  | 2 | QA testing: broken links, forms, tracking, cross-browser check, SEO metadata, image optimisation. | Purnima | Self | 2025-12-26 | 2026-02-27 | 64 | Not Started
| Launch & Post-launch Enhancements | 1 | Launch updated site and monitor performance for 30 days. | Purnima | Self | 2025-12-26 | 2026-02-27 | 64 | Not Started
|  | 2 | Optimise based on analytics: top menu improvements, homepage adjustments, page optimisation, bounce-rate reduction. | Purnima | Self | 2025-12-26 | 2026-02-27 | 64 | Not Started
Services Newsletter & Client Calendar Templates (2-page templates) | Template Strategy | 1 | Map content requirements for the 2-page monthly Services Newsletter & Calendar (events, support groups, counselling updates, etc.). | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
|  | 2 | Align template design with ARC’s brand colours, typography, and messaging tone. | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
| Design & Build | 1 | Create visually clean 2-page templates for: Monthly service calendar, Monthly client newsletter | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
|  | 2 | Ensure templates meet accessibility standards (contrast, readability, image alt text). | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
| Integration & Automation | 1 | Integrate templates into HubSpot for easy updating by Services team. | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
|  | 2 | Connect with Salesforce segmentation so the right clients receive the right information. | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
| Pilot & Refine | 1 | Pilot templates for 2 months → collect feedback → refine visual hierarchy, clarity, and layout | Purnima | Self | 2025-11-21 | 2025-11-28 | 8 | In Progress
Legacy in Will – Upgrade Strategy | Audit & Benchmarking | 1 | Review existing ARC Legacy in Will materials (PDFs, web pages, brochures). | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
|  | 2 | Benchmark against other leading Irish/UK charities’ legacy programmes. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
| Messaging & Creative | 1 | Develop refined messaging: storytelling, impact statements, donor stories, FAQs. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
|  | 2 | Create updated brand-aligned visuals and downloadable assets. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
| Digital Presence Upgrade | 1 | Edit the existing dedicated Legacy in Will landing page with clear “next steps” and contact info. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
|  | 2 | Add accessible video content explaining how legacy gifts help ARC. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
| Donor Journey & Automation | 1 | Design an automated journey for legacy enquiries (welcome email, follow-up resources, thank-you note). | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
|  | 2 | Sync journey steps with Salesforce tagging and reporting. | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
| Promotion & Awareness | 1 | Launch multi-channel awareness campaign (email, social, website). | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
|  | 2 | Include Leagcy in Will Drip-Drip messaging in very communication acroos all channels | Purnima | Self | 2025-12-01 | 2025-12-30 | 30 | Not Started
Digital Tracking Across All Channels | Audit | 1 | Audit all existing tracking: website, social media, email, events, donations. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Identify missing tracking areas (e.g., event RSVPs, downloads, volunteer forms). | Purnima | Self | 2025-11-21 |  |  | In Progress
| Website & Platform Tracking | 1 | Implement enhanced tracking via: HubSpot tracking code, Google Analytics, Meta Pixel, LinkedIn Insights Tag. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Tag all key events: form submissions, bookings, button clicks, video views. | Purnima | Self | 2025-11-21 |  |  | In Progress
| CRM & Automation Tracking | 1 | Ensure HubSpot ↔ Salesforce events are tracked correctly (thanks to API access). | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Build dashboards for: client engagement, donor behaviour, volunteer activity. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Reporting | 1 | Create monthly digital performance reports. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Identify trends & optimise campaigns accordingly. | Purnima | Self | 2025-11-21 |  |  | In Progress
AI Enablement & Intelligent Automation | AI Audit & Opportunity Mapping | 1 | Identify where AI can support ARC’s operations, e.g.:1. 1.Content creation (blogs, social media, newsletters) 2.Service information updates 3.Segmentation recommendations 4. Donor insights & predictive analytics 5. Website personalisation 6. Admin workflows (summaries, tasks) | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Document current pain points (manual tasks, delays, repetitive content work, donor follow-up gaps). | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 3 | Define AI use cases that are safe, ethical, and high-impact. | Purnima | Self | 2026-01-02 |  |  | Not Started
| AI Tools & Governance Setup | 1 | Select recommended tools: a.ChatGPT / GPT for content and research b.HubSpot AI for emails, social posts, and predictive segments c.Salesforce Einstein for donor insights and automation d.Canva AI tools for design support | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Develop AI guidelines: Tone of voice Ethical standards Confidentiality rules Verification & fact-checking procedures | Purnima | Self | 2026-01-02 |  |  | Not Started
| Workflow Integration | 1 | Integrate AI into daily and weekly workflows, e.g.: a. Drafting newsletters, social posts, blogs b. Summarising client or donor conversations for reports c. Creating event descriptions, templates, calendars d. Drafting campaign messaging and appeal letters e. First-draft copy for fundraising materials | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Use AI to shortcut content production while keeping final human review for quality and compliance. | Purnima | Self | 2026-01-02 |  |  | Not Started
| Intelligent Automation & Insights | 1 | Use AI for predictive insights, such as: a. Donor likelihood to give again b. Identifying high-engagement clients or supporters c. Suggesting optimal send times for communications d. Predicting which content performs best | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Use AI to improve service delivery: a. Automated FAQs b. AI-generated appointment reminders c. Suggested responses for the Services team (human approved) | Purnima | Self | 2026-01-02 |  |  | Not Started
| Training, Quality Control & Monitoring | 1 | Train staff on: a. How to use AI tools b. When NOT to use AI c. How to fact-check AI outputs d. How to maintain the ARC tone of voice | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Create a monthly AI review cycle to ensure: a. Outputs remain accurate b. Brand consistency is maintained c. AI-generated recommendations are improving performance | Purnima | Self | 2026-01-02 |  |  | Not Started
Develop and execute an integrated marketing, awareness, communications, and digital strategy | Audit & Planning | 1 | Review what exists right now across marketing, awareness, communications, and digital. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Identify gaps that stop us from reaching organisational goals. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Strategy Creation | 1 | Build an integrated plan that links digital, comms, fundraising, brand, and service messaging. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Define budgets and resources needed. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Implementation | 1 | Roll out activities across website, social, email, print, PR, and campaigns. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Match everything with ARC’s values and mission. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Review & Adaptation | 1 | Evaluate what worked and what didn’t. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Refine strategy every quarter. | Purnima | Self | 2025-11-21 |  |  | In Progress
Manage digital presence and engagement | Review Current Digital Presence | 1 | Analyse existing social media, website, interactions, and responses. | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Identify improvement areas and missing pieces. | Purnima | Self | 2026-01-02 |  |  | Not Started
| Engagement Planning | 1 | Build a plan for consistent posting, follower interaction, and responding to queries. | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Use new ideas to improve ARC’s voice online. | Purnima | Self | 2026-01-02 |  |  | Not Started
| Execution | 1 | Manage content calendars, social posts, and website updates. | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Coordinate with internal teams. | Purnima | Self | 2026-01-02 |  |  | Not Started
| Measurement | 1 | Agree on digital engagement metrics (followers, interactions, response time). | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Track the results weekly/monthly. | Purnima | Self | 2026-01-02 |  |  | Not Started
Oversee the creative development process | Briefing & Planning | 1 | Set campaign goals for December and Christmas. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Create briefs for design, messaging, and storytelling. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Creative Development | 1 | Work with internal teams and external contractors. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Review drafts, messaging, visuals, and content. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Execution | 1 | Manage timelines, approvals, and production. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Coordinate print, fulfilment, and digital rollout. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Post-campaign review | 1 | Analyse performance, donations, engagement. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Document learnings for 2026. | Purnima | Self | 2025-11-21 |  |  | In Progress
Maintain brand consistency across all communications | Brand Review | 1 | Evaluate existing materials for inconsistencies. | Purnima | Self | 2026-02-02 |  |  | Not Started
|  | 2 | Identify tone of voice gaps and design mismatches. | Purnima | Self | 2026-02-02 |  |  | Not Started
| Brand Standards | 1 | Ensure visual identity, tone, and messaging stay aligned. | Purnima | Self | 2026-02-02 |  |  | Not Started
|  | 2 | Prioritise brand alignment for September newsletter. | Purnima | Self | 2026-02-02 |  |  | Not Started
| Ongoing Implementation | 1 | Guide all teams to use the correct templates. | Purnima | Self | 2026-02-02 |  |  | Not Started
|  | 2 | Audit new output regularly. | Purnima | Self | 2026-02-02 |  |  | Not Started
Create and oversee compelling marketing content | Content Planning | 1 | Build a cross-channel content plan (social, email, website, print). | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Align content with ARC values and mission. | Purnima | Self | 2025-12-01 |  |  | Not Started
| Content Development | 1 | Write, design, and create content. | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Use stories, impact updates, and real voices. | Purnima | Self | 2025-12-01 |  |  | Not Started
| Distribution | 1 | Share content across key channels. | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Repurpose content to reach more audiences. | Purnima | Self | 2025-12-01 |  |  | Not Started
Plan and assist execution of multi-channel fundraising & awareness campaigns | Campaign Planning | 1 | Create marketing and comms plan for Q1 2026. | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Begin early planning for 2026 campaigns. | Purnima | Self | 2025-12-01 |  |  | Not Started
| Execution | 1 | Roll out across ATL, BTL, digital, and experiential channels. | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Coordinate with fundraising, services, and external partners. | Purnima | Self | 2025-12-01 |  |  | Not Started
| Reporting | 1 | Track engagement and donations. | Purnima | Self | 2025-12-01 |  |  | Not Started
|  | 2 | Document what worked for next year. | Purnima | Self | 2025-12-01 |  |  | Not Started
Lead donor communications and stewardship | Story Gathering | 1 | Collect stories/testimonials (set a metric/target | Purnima | Self | 2025-11-21 |  |  | In Progress
| Donor Communication Plan | 1 | Set rhythm for donor updates (monthly, quarterly, campaign-based) | Purnima | Self | 2025-11-21 |  |  | In Progress
| Execution | 1 | Create heartfelt stories, impact reports, thank-you updates. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Build trust and long-term supporter engagement. | Purnima | Self | 2025-11-21 |  |  | In Progress
Monitor, analyse, and report on performance | Set KPIs | 1 | Agree on metrics for awareness, marketing, fundraising. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Include special focus on Christmas campaign. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Tracking Setup | 1 | Ensure platforms track all digital actions. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Compile results from social, email, website, CRM. | Purnima | Self | 2025-11-21 |  |  | In Progress
| Reporting | 1 | Create monthly dashboards. | Purnima | Self | 2025-11-21 |  |  | In Progress
|  | 2 | Use data to refine communications and improve ROI. | Purnima | Self | 2025-11-21 |  |  | In Progress
Support delivery of key organisational and fundraising events | Event Planning Support | 1 | Create event marketing and PR plans. | Purnima | Self | 2026-03-02 |  |  | Not Started
|  | 2 | Coordinate internal and external messaging. | Purnima | Self | 2026-03-02 |  |  | Not Started
| Promotion | 1 | Push event awareness across all channels. | Purnima | Self | 2026-03-02 |  |  | Not Started
|  | 2 | Support Services and Fundraising teams. | Purnima | Self | 2026-03-02 |  |  | Not Started
| Engagement Tracking | 1 | Monitor RSVPs, engagement, and outcomes. | Purnima | Self | 2026-03-02 |  |  | Not Started
Manage relationships with third-party agencies and suppliers | Relationship Review | 1 | Identify current suppliers (print, fulfilment, designers, Yellow Harbour). | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Clarify responsibilities. | Purnima | Self | 2026-01-02 |  |  | Not Started
| Collaboration | 1 | Ensure smooth workflow and communication. | Purnima | Self | 2026-01-02 |  |  | Not Started
|  | 2 | Maximise value from partnerships. | Purnima | Self | 2026-01-02 |  |  | Not Started
Oversee the marketing budget | Budget Review | 1 | Review 2026 marketing budget for each key priorities | Purnima | Self | 2025-12-01 |  |  | Not Started
| Cost Planning | 1 | Plan for campaigns, website updates, design work, printing, digital tools. | Purnima | Self | 2025-12-01 |  |  | Not Started
| Monitoring | 1 | Ensure campaigns stay within budget while still making impact. | Purnima | Self | 2025-12-01 |  |  | Not Started

## CRM Improvements
CRM Improvements (incl. Audit, Data, Automation, Training)
CRM Focus Areas | CRM audit, data hygiene, segmentation, automation flows, integrated communications, reporting, and staff training to strengthen and streamline all CRM processes
Goals & KPIs | Improve engagement, reduce manual work through automation, enhance communication quality, and strengthen reporting to support fundraising and service decisions
Scope | Includes CRM audit, data cleanup, automation, segmentation, integrations, template updates, training, and reporting, while excluding major system migrations, website rebuilds, organisational policy changes, and large-scale IT development.
Stakeholder List | Purnima, Hannah
Risks & Dependencies | Risk of compliance & Dependencies of Access levels.
Workstream | Phase | Sub Phase | # | Steps | Assigned to | Start Date | Completed by | Duration (days) | Status | RAG | Priority | % Complete | Notes
Sending timely thank-you notes, event follow-ups, and appeal updates automatically. | Automated communication | Audit & Mapping | 1 | Document every type of thank-you note, follow-up and appeal update currently sent. | Purnima | 2026-01-05 | 2026-01-09 | 5 | Not Started | Green | Medium
|  |  | 2 | Map which ones come from HubSpot vs. Salesforce. | Purnima | 2026-01-05 | 2026-01-09 | 5 | Not Started | Green | Medium
|  |  | 3 | Identify triggers (donation received, event attended, enquiry submitted). | Purnima | 2026-01-05 | 2026-01-09 | 5 | Not Started | Green | Medium
|  | Data & Integration Plan | 1 | Confirm where donor/contact “source of truth” should live (likely Salesforce) | Purnima | 2026-01-05 | 2026-01-09 | 5 | Not Started | Green | Medium
|  |  | 2 | Decide whether HubSpot → Salesforce → HubSpot sync is needed. | Purnima | 2026-01-12 | 2026-01-13 | 2 | Not Started | Green | Medium
|  |  | 3 | Set required fields for automation (email, name, donation amount, event type). | Purnima | 2026-01-14 | 2026-01-15 | 2 | Not Started | Green | Medium
|  | Build Automation Flows | 1 | In HubSpot: build email automation flows triggered by form submissions or lists. | Purnima | 2026-01-16 | 2026-01-20 | 5 | Not Started | Green | Medium
|  |  | 2 | In Salesforce: build workflows for donations/events logged in Salesforce. | Purnima | 2026-01-21 | 2026-01-23 | 3 | Not Started | Green | Medium
|  |  | 3 | Set up the HubSpot–Salesforce connector (supported because API access is enabled) | Purnima | 2026-01-26 | 2026-01-28 | 3 | Not Started | Green | Medium
|  | Testing & Launch | 1 | Test every automation with sample data | Purnima | 2026-01-29 | 2026-01-31 | 3 | Not Started | Green | Medium
|  |  | 2 | Check personalisation tokens pull correctly. | Purnima | 2026-01-29 | 2026-01-31 | 3 | Not Started | Green | Medium
|  |  | 3 | Go live in small batches, then fully launch. | Purnima | 2026-01-29 | 2026-01-31 | 3 | Not Started | Green | Medium
Streamlining service updates and newsletters so our clients, volunteers, and partners stay better informed. | Streamlined updates & newsletters | Audience Segmentation | 1 | Define groups: clients, volunteers, partners, donors, staff. | Purnima | 2026-02-02 | 2026-02-06 | 5 | Not Started | Green | Medium
|  |  | 2 | Map where these groups currently live (HubSpot? Salesforce? Both?). | Purnima | 2026-02-02 | 2026-02-06 | 5 | Not Started | Green | Medium
|  | Data Cleanup | 1 | Clean up duplicates and inconsistent tags. | Hannah | 2026-02-09 | 2026-02-20 | 12 | Not Started | Green | Medium
|  |  | 2 | Create a standard tagging method (e.g., “Client – Rathgar”, “Volunteer – Events”). | Hannah | 2026-02-09 | 2026-02-20 | 12 | Not Started | Green | Medium
|  | Email System Decision | 1 | Option A: Send newsletters from HubSpot (recommended — website + forms are already there). | Purnima | 2026-02-23 | 2026-02-23 | 1 | Not Started | Green | Medium
|  |  | 2 | Option B: Send from Salesforce Marketing Cloud/Pardot | Purnima | 2026-02-23 | 2026-02-23 | 1 | Not Started | Green | Medium
|  | Build Newsletter Workflows | 1 | Set up lists synced from CRM tags. | Purnima | 2026-02-24 | 2026-02-27 | 4 | Not Started | Green | Medium
|  |  | 2 | Create reusable templates (updates, service announcements, volunteer news). | Purnima | 2026-03-02 | 2026-03-06 | 5 | Not Started | Green | Medium
|  |  | 3 | Schedule recurring communication rhythms (monthly, quarterly, etc.). | Purnima | 2026-03-02 | 2026-03-06 | 5 | Not Started | Green | Medium
Making it easier to segment our contacts, so people only get the information that’s relevant to them. | Better segmentation | Segmentation Framework | 1 | Create a standard list of segments needed (clients, volunteers, donors, partners). | Purnima | 2026-03-09 | 2026-03-11 | 3 | Not Started | Green | Medium
|  |  | 2 | Agree on definitions and what qualifies someone for each segment. | Purnima | 2026-03-09 | 2026-03-11 | 3 | Not Started | Green | Medium
|  | Tagging Rules | 1 | Create tagging fields in Salesforce (primary database). | Purnima | 2026-03-09 | 2026-03-11 | 3 | Not Started | Green | Medium
|  |  | 2 | Mirror essential tags in HubSpot if HubSpot sends communications. | Purnima | 2026-03-09 | 2026-03-11 | 3 | Not Started | Green | Medium
|  |  | 3 | Define who is responsible for assigning tags (Purnima/Hannah/Stephanie). | Purnima | 2026-03-09 | 2026-03-11 | 3 | Not Started | Green | Medium
|  | Automation-Based Segmentation | 1 | Build rules where form submissions automatically tag people (HubSpot). | Purnima | 2026-03-12 | 2026-03-17 | 6 | Not Started | Green | Medium
|  |  | 2 | Donations or volunteer sign-ups automatically tag people (Salesforce). | Purnima | 2026-03-12 | 2026-03-17 | 6 | Not Started | Green | Medium
|  |  | 3 | Sync tags between Salesforce ↔ HubSpot via integration where needed. | Purnima | 2026-03-12 | 2026-03-17 | 6 | Not Started | Green | Medium
|  | Dashboard & Quality Checks | 1 | Review segmentation accuracy monthly. | Purnima | 2026-03-12 | 2026-03-17 | 6 | Not Started | Green | Medium
|  |  | 2 | Run reports on missing/untagged contacts. | Purnima | 2026-03-12 | 2026-03-17 | 6 | Not Started | Green | Medium
Tracking engagement, so we can see what’s working and keep improving. | Engagement tracking | Define Key Engagement Metrics | 1 | Email opens, click rates, event attendance, donation frequency. | Purnima | 2026-03-18 | 2026-03-20 | 3 | Not Started | Green | Medium
|  |  | 2 | Service use engagement (class attendance, counselling sessions). | Purnima | 2026-03-18 | 2026-03-20 | 3 | Not Started | Green | Medium
|  | Enable Tracking Tools | 1 | Add HubSpot tracking code to website. | Purnima | 2026-03-23 | 2026-03-24 | 2 | Not Started | Green | Medium
|  |  | 2 | Ensure Salesforce fields capture donations, events, volunteer hours. | Purnima | 2026-03-23 | 2026-03-24 | 2 | Not Started | Green | Medium
|  | Build Dashboards | 1 | In HubSpot: email performance, website engagement. | Purnima | 2026-03-25 | 2026-03-27 | 3 | Not Started | Green | Medium
|  |  | 2 | In Salesforce: donor retention, appeals performance, volunteer activity. | Purnima | 2026-03-25 | 2026-03-27 | 3 | Not Started | Green | Medium
|  | Insights & Continuous Improvement | 1 | Hold monthly CRM review sessions. | Purnima | 2026-03-30 | 2026-03-31 | 2 | Not Started | Green | Medium
|  |  | 2 | Adjust automations and messaging based on data trends. | Purnima | 2026-03-30 | 2026-03-31 | 2 | Not Started | Green | Medium
|  |  | 3 | Identify drop-off points (e.g., people opening emails but not clicking). | Purnima | 2026-03-30 | 2026-03-31 | 2 | Not Started | Green | Medium

## Overview
Digital Marketing & CRM – 2026 Project Portfolio
Last updated: | 13:36
Instructions
1. Use each project tab to capture detailed tasks, owners, dates and risks.
4. You can add PivotTables and dashboards on new sheets using the tables already created.